## Instructions
MVP Solution Architecture & Effort Sizing — Instructions
| Purpose | This workbook captures the solution architecture for an MVP and produces an effort estimate based on a single developer's inventory. Fill the yellow cells. Green cells calculate automatically. The Effort Summary sheet rolls up totals.
| How to use | 1. Fill the Project Info sheet (project name, dates, demo target). 2. List every Screen on the Screens sheet — purpose, functionality, current vs target state. 3. List every Backend Service / API on the Backend Services sheet. 4. List every Microservice and Integration on the Microservices & Integrations sheet. 5. For each item, set Status and Complexity. Estimated Days auto-fills from Complexity. 6. Override the Estimated Days column manually whenever you have a better number. 7. Review the Effort Summary sheet — it aggregates the entire workbook.
Color legend
| Yellow | Input cell — fill this in.
| Green | Calculated — formula will fill it for you.
| Status values | Not Started • In Progress • Blocked • Done Use the dropdown in the Status column.
| Complexity scale | S = Small, ~1 dev-day (trivial change, simple CRUD endpoint, basic screen) M = Medium, ~3 dev-days (standard feature with some logic) L = Large, ~8 dev-days (multi-component feature, non-trivial integration) XL = X-Large, ~15 dev-days (new service, complex flow, heavy unknowns) These defaults are conservative for a single developer. Override the Estimated Days column whenever you have a better number from a spike or prior experience.
| Tip | If a row represents work that is already Done, set Status = Done. Done items are excluded from the 'Remaining' totals on the Effort Summary so you can see exactly how much is left to reach the demo.

## Project Info
Project Information
| Project / MVP name | Aurion Clinical AI — MVP (Clinic Mode, CREOQ/CLLC pilot)
| Developer (owner) | Faïçal Sawadogo (CTO / sole developer)
| Today's date | 2026-05-14
| Target demo date | 2026-07-15
| Working days available | 44
| Demo audience / stakeholder | Dr. Perry Gdalevitch (plastic surgery) + Dr. Marie Gdalevitch (orthopedic surgery), CREOQ/CLLC pilot
| Primary business goal | Prove a wearable multimodal AI scribe can produce traceable, descriptive-mode clinical notes safely enough to run a 3–5 clinician pilot.
| In-scope for demo (one line) | Consent → record → transcript → Stage 1 → Stage 2 vision → review with conflict resolution → DOCX/text export → audited local purge. iPhone/iPad fallback (Ray-Ban Meta deferred).
| Explicitly out-of-scope | Ray-Ban Meta SDK (M-03 deferred), EMR/FHIR integration, Post-Op/Procedural Mode, French support, full Web Patient Chart Workspace, Schedule, Templates CRUD UI, fine-tuning, diagnostic inference, Android.
| Tech stack (frontend) | SwiftUI universal iOS app (iPhone + iPad), iOS 16+, A15 Bionic min. Apple Vision + ReplayKit + AVFoundation for capture/masking.
| Tech stack (backend) | Python 3.12, FastAPI, SQLAlchemy async, PostgreSQL, Pydantic v2. Provider registry abstracts OpenAI / Anthropic / Gemini for note-gen + vision; Whisper / AssemblyAI for transcription.
| Hosting / infra | AWS ca-central-1: S3 (frames, audio), DynamoDB (audit log), AppConfig (runtime config), Cognito (auth), KMS, Textract (screen OCR), Secrets Manager. LocalStack for dev. Terraform/HCL IaC.
| Known risks / unknowns | (1) No Alembic migrations — P0-04 outstanding. (2) Admin users + eval scores still in-memory — P0-06. (3) End-to-end smoke test missing — P0-07. (4) Stage 2 background task is fire-and-forget; no recovery sweep for abandoned jobs. (5) Hand-rolled DOCX writer untested against full Word fidelity.
Current State → Target State (high-level narrative)
| Current state | Backend (FastAPI) has full session lifecycle, transcription, Stage 1 + Stage 2 note generation, screen OCR, vision conflict detection, async Stage 2 jobs, on-device export audit, and immutable audit log. 200 unit tests passing. iOS app covers onboarding (incl. voice enrollment), capture (audio/video/screen), on-device PHI masking (fail-closed, P0-01/02), Stage 1 SLA instrumentation, note review with conflict resolution + source badges, on-device DOCX/plain-text export with audited local purge, iPad-adaptive layouts. Web portal scaffolds: dashboard, audit, masking report, eval, config, users (mock).
| Target state for demo | One clinician completes a full encounter on iPhone or iPad: consent gate enforces, audio/video/screen capture, Stage 1 < 30 s, Stage 2 enrichment lands async, conflicts resolved explicitly, DOCX/text exported on-device, local data purged with audit confirmation. 3–5 clinicians run this in clinic during the pilot week.
| Gap (what must be built) | Alembic migrations (P0-04, XL); persistent user + eval store (P0-06, L); E2E smoke test script (P0-07, M); web note-review UI (W-04, L, post-pilot acceptable); patient/schedule/templates (B-01/B-02/B-03, post-pilot).

## Effort Summary
Effort Summary — Rolled Up
Area | Items planned | Items done | Total effort (days) | Remaining (days) | % remaining | % remaining
Screens
Backend Services
Microservices & Integrations
GRAND TOTAL
Calendar conversion
| Buffer / contingency % | 20% | default 20% — edit to your taste
| Productive days / week | 4 | meetings/email eat the rest
Remaining effort (days)
With buffer (days)
Calendar weeks needed
Note: All numbers on this sheet are formulas pulling from the other tabs. Update the source sheets and these totals update automatically.

## Screens
Screens — UI Inventory
ID | Screen Name | User / Role | Purpose | Key Functionality (bullets) | Inputs / Data shown | Backend services it calls | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
S001 | SplashView | All | Cold-start splash + auth-routing decision | Logo reveal / auth check / route to login or main tab | AuthState from Keychain | B001 Auth | Built | Built — no demo change | P2 | Done | S |  |  |  | — | — | Animation polish only.
S002 | AuthView + LoginView + RegisterView | Clinician | Sign-in / sign-up gate, JWT obtain | Email+password / register / forgot-flow stub | Email, password | B001 Auth | Built | Built | P0 | Done | M |  |  |  | B001 | — | Cognito JWKS validation server-side.
S003 | BiometricConsentView | Clinician (onboarding) | Explicit consent for voice biometric enrollment | Show policy / require explicit accept / log audit | Toggle + consent text | — | Built | Built | P0 | Done | S |  |  |  | — | — | biometric_consent_confirmed audit event.
S004 | VoiceExplanationView | Clinician (onboarding) | Explain voice enrollment purpose pre-recording | Static explanatory copy + Continue CTA | — | — | Built | Built | P1 | Done | S |  |  |  | — | — | —
S005 | VoiceRecordingView | Clinician (onboarding) | Capture 4 enrollment sentences for speaker tagging | 4 prompts / waveform / re-record / silent detection | Microphone PCM | — | Built (M-01 reconciled embedding dims) | Built | P0 | Done | L |  |  |  | S005 | — | Raw audio deleted immediately after embedding compute.
S006 | VoiceProcessingView | Clinician (onboarding) | Compute 128-dim MFCC embedding + persist to Keychain | Progress ring / extract embedding / Keychain write / audit | Recorded WAV from S005 | — | Built | Built | P0 | Done | M |  |  |  | S005 | — | Embedding never transmitted to backend.
S007 | WearableSetupView | Clinician (onboarding) | Optional Ray-Ban Meta pairing + iPhone fallback | BLE scan UI / paired devices / fallback explainer | BLE state | — | Stubbed (M-03 deferred) | Show iPhone-fallback explainer; pairing UI hidden behind dev flag | P2 | Done | M |  |  |  | M019 Meta SDK | Meta SDK access pending partner approval | iPhone/iPad path is the pilot scope.
S008 | OnboardingFlowView | Clinician | Orchestrates the 6-step onboarding stepper | Step state machine / progress dots / back nav / skip | Stepper state | — | Built | Built | P0 | Done | M |  |  |  | S003–S007 | — | —
S009 | PhysicianProfileSetupView | Clinician (onboarding) | Capture practice type, primary specialty, consent prefs | Form: practice type / specialty / language / defaults | Profile fields | B002 Profile | Built | Built; iPad-adaptive padding added M-13 | P0 | Done | M |  |  |  | B002 | — | —
S010 | MainTabView | Clinician | Tab shell: Dashboard / Devices / Profile | Tab bar / route preservation / badge on pending sessions | — | — | Built | Built | P0 | Done | S |  |  |  | S011, S013, S017 | — | —
S011 | DashboardView | Clinician | Home — start session, recent sessions, Stage 2 status tiles | Start session CTA / mode picker / recent sessions list / continue-recording card / processing tiles | Session list + active session | B006 Sessions, B010 Notes (stage2-status) | Built | Add Stage 2 pending tile from polling endpoint (M-07 surface; partial — currently in NoteReviewView only) | P0 | Done | M |  |  |  | B006, B010, M021 | Stage 2 pending UI on Dashboard not yet built (deferred to post-pilot polish). | iPad-adaptive padding M-13.
S012 | CaptureView | Clinician | Pre-encounter consent gate + record / pause / resume / stop, three streams | Consent picker (verbal/paper/digital) / record CTA / mode chips / live waveform / live caption / pause+resume / stop | Mic, camera, screen frames | B006 Sessions, B007 Transcription, B008 Frames, B009 Screen | Built (M-02/M-05/M-06 done) | Built | P0 | Done | XL |  |  |  | S007 Devices, M015 Apple Vision, M016 AVFoundation, M017 ReplayKit | Permission denial path needs visual QA on iPad. | Hard-blocks record until consent_confirmed audit event written.
S013 | DeviceHubView | Clinician | Inspect mic/camera/screen permissions + BLE devices + diagnostics | Sources list / permissions grid / pairing actions / test-frame | Permission state | — | Built | Built; iPad-adaptive M-13 | P1 | Done | M |  |  |  | M020 BLE | — | —
S014 | PostEncounterView | Clinician | Confirm specialty template + encounter type before pipeline kicks off | Template picker / encounter type chips / Generate CTA | Specialty, encounter type, allied health | B010 Notes | Built | Built | P0 | Done | M |  |  |  | B010 | — | —
S015 | ProcessingView (inside ContentView) | Clinician | Stage 1 in-flight + retry surface + masking-failure prompt | Spinner / status text / Stage 1 retry / masking retry+skip / 30 s timeout | Stage1Status, masked-frame failures | B007 Transcription, B010 Notes | Built (M-06 SLA + retry) | Built | P0 | Done | L |  |  |  | B007, B010 | — | Tracks record-stop → note-ready latency for pilot metrics.
S016 | NoteReviewView | Clinician | Stage 1/Stage 2 review with source citations + conflict resolution + per-section edit + final approval | Prose body / SOURCES panel (T/V/S/E badges) / EDITED indicator / conflict Accept/Reject/Edit / edit sheet / Stage 2 banner / approve flow | NoteResponse + WebSocket updates | B010 Notes, B011 Vision, B014 WebSocket | Built (M-09 source anchoring, M-10 conflicts, M-07 Stage 2 banner) | Built | P0 | Done | XL |  |  |  | B010, B011 | Conflict-resolution flow needs clinician usability pass during dry run. | iPad: prose body capped at 720pt for readable line length.
S017 | ExportView | Clinician | On-device DOCX + plain text export, share, audited local purge | Format picker (DOCX / Text; PDF deferred) / on-device generate / share sheet / purge confirmation chip / audit POST | Latest NoteResponse | B010 Notes (full), B012 Export (audit) | Built (M-11 on-device gen, M-12 purge integration) | Built | P0 | Done | L |  |  |  | B012, M015 | DOCX is hand-rolled minimal ZIP; verify Word fidelity on actual desktop. | PDF flagged Coming Soon; not in MVP.
S018 | NoteReadyView | Clinician | Brief 'Stage 1 ready' banner that opens review | Toast / Open CTA / dismiss | — | — | Built | Built | P1 | Done | S |  |  |  | S014, S015 | — | —
S019 | SessionsInboxView | Clinician | Past sessions — completeness scores, drill into note | Session list / sort / filter / open SessionNoteView | Sessions list | B006 Sessions, B010 Notes | Built | Built; iPad-adaptive M-13 | P1 | Done | M |  |  |  | B006 | — | —
S020 | SessionNoteView | Clinician | Read-only past note with source citation drilldown | Section list / source panel / edit (if re-open) / share | NoteResponse | B010 Notes | Built | Built | P1 | Done | M |  |  |  | B010 | — | Re-uses NoteReviewView styling.
S021 | ProfileView | Clinician | Settings — profile, voice profile mgmt, language, privacy, retention prefs, sign out | Profile read/edit / voice profile status + delete+re-enroll / language picker / sign out | Profile fields | B002 Profile | Built | Built | P1 | Done | M |  |  |  | B002 | — | Voice-profile-deleted audit event.
S022 | FrameGalleryView (debug) | Developer | Inspect captured masked frames for QA | Grid of thumbnails / tap to preview / discard | CapturedFrame list | — | Built | Hidden in pilot/release builds | P3 | Done | S |  |  |  | — | Confirm guarded behind #if DEBUG. | Visible only in dev — keep out of pilot UX.
S023 | ContentView (root shell) | All | Top-level router — auth → onboarding → main app, plus recovery flow | Routing tree / processing overlay / scene-phase hooks (M-12 stale purge) | — | — | Built | Built | P0 | Done | M |  |  |  | S001, S002, S008 | — | scenePhase=.active fires LocalDataPurger.purgeStaleArtifacts().
S024
S025
TOTAL (days)
REMAINING (days, excl. Done)
Note on L3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.

## Backend Services
Backend Services & APIs
ID | Service / Module Name | Type | Purpose | Endpoints / Functions (list) | Data model / entities | Data store | Auth required? | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
B001 | Auth (api/v1/auth.py) | API | Sign-up / login / JWT / dev seed users | POST /auth/login, /auth/register, /auth/me, seed_dev_users (dev) | UserModel | PostgreSQL + Cognito JWKS | No (login) / Yes (rest) | Built | Built | P0 | Done | M |  |  |  | B021 SessionMgr | — | —
B002 | Profile (api/v1/profile.py) | API | Physician profile CRUD | GET/PUT /profile, /profile/specialties | PhysicianProfileModel | PostgreSQL | Yes | Built | Built | P0 | Done | S |  |  |  | — | — | —
B003 | Config (api/v1/config.py) | API | Expose runtime AppConfig (providers, flags) to clients | GET /config | AppConfig schema | AWS AppConfig (LocalStack in dev) | Yes | Built | Built | P1 | Done | S |  |  |  | M008 AppConfig | — | 30 s polling on backend.
B004 | Admin (api/v1/admin.py) | API | Admin endpoints: audit, masking report, metrics, sessions, users, eval, config | GET /admin/* (audit, masking-report, sessions, users, eval-scores) | _MOCK_USERS (in-memory!) | PostgreSQL + DynamoDB + memory | Yes (admin role) | Built but users + eval-scores are in-memory mocks | Replace mock users + eval scores with persistent storage (P0-06). | P0 | Done | L |  |  |  | B026 user store, B027 eval scores | P0-06 blocker for compliance audit pre-pilot. | Visible to ADMIN + COMPLIANCE_OFFICER + EVAL_TEAM.
B005 | Privacy (api/v1/privacy.py) | API | PHI masking report aggregating audit-log proofs | GET /privacy/masking-report | Audit events (DynamoDB) | DynamoDB | Yes | Built | Built | P0 | Done | M |  |  |  | B018 audit-log | — | Proves 100% on-device masking pre-transmission.
B006 | Sessions (api/v1/sessions.py) | API | Session lifecycle: create / consent / start / pause / resume / stop / status; consent metadata capture | POST /sessions, /confirm-consent, /start, /pause, /resume, /stop; GET /sessions/{id} | SessionModel, audit events | PostgreSQL + DynamoDB | Yes | Built (M-05 paper-consent metadata wired) | Built | P0 | Done | L |  |  |  | B021 state-machine | — | Consent hard-block in audit_log gate.
B007 | Transcription (api/v1/transcription.py) | API | WAV upload → Whisper → transcript persist → PHI audit → Stage 1 trigger; speaker tags PATCH; SLA latency capture | POST /transcription/{id}; PATCH /transcription/{id}/speakers | TranscriptModel, PilotMetricsModel, TranscriptSegment[] | PostgreSQL + S3 | Yes | Built (M-01 speaker tags + M-06 SLA) | Built | P0 | Done | XL |  |  |  | B015 providers, M001 Whisper | — | Wall-clock 30 s SLA via URLSession timeoutIntervalForResource.
B008 | Frames (api/v1/frames.py) | API | Masked video frame upload with masking proof contract (P0-02) | POST /frames/{id} | S3 keyed frames; audit | S3 + DynamoDB | Yes | Built | Built | P0 | Done | M |  |  |  | B018 audit-log | — | Rejects uploads without verifiable masking metadata.
B009 | Screen (api/v1/screen.py) | API | Screen frame upload + on-device redaction proof; OCR + extracted lab/imaging merge into note (B-05) | POST /screen/{id} | ScreenCaptureResult, NoteClaim | S3 + PostgreSQL (note version) | Yes | Built (B-05 + M-08 vertical slice) | Built | P0 | Done | L |  |  |  | B010 Notes, B019 PHI-audit, M011 Textract | — | Stage 1 must exist before merge — append-only into target section.
B010 | Notes (api/v1/notes.py) | API | Stage 1 read / approve-stage1 (now async) / Stage 2 detail / conflict resolve / edit / approve final / Stage 2 status (B-04) | GET /notes/{id}/stage1, /detail, /full, /stage2-status; POST /approve-stage1, /approve; PATCH /edit, /conflicts/{cid}/resolve | Note, NoteVersionModel, Stage2JobModel | PostgreSQL | Yes | Built (M-09 schema + B-04 detail endpoint + M-10 resolve + B-06 async) | Built | P0 | Done | XL |  |  |  | B011 Vision, B022 Versioning, B023 Stage 2 jobs | — | approve-stage1 dispatches Stage 2 via asyncio.create_task; fire-and-forget by design.
B011 | Vision (api/v1/vision.py) | API | Stage 2 visual enrichment: retrieve frames → caption → classify ENRICHES/REPEATS/CONFLICTS → merge | POST /vision/{id} (also called from approve-stage1 background task) | FrameCaption[], conflict claims | S3 + PostgreSQL | Yes | Built | Built | P0 | Done | XL |  |  |  | B016 vision providers | — | Now invoked from Stage 2 job background task, not inline.
B012 | Export (api/v1/export.py) | API | Server-side DOCX (web portal) + on-device audit endpoint (B-09) | POST /notes/{id}/export, /notes/{id}/export-audit | Audit events; session state transitions | DynamoDB + PostgreSQL | Yes | Built (B-09 audit endpoint added) | Built | P0 | Done | M |  |  |  | B020 Cleanup | — | Transitions REVIEW_COMPLETE → EXPORTED idempotently.
B013 | Health (api/v1/health.py) | API | Liveness probe for ECS/ALB | GET /health | — | — | No | Built | Built | P1 | Done | S |  |  |  | — | — | —
B014 | WebSocket (api/v1/websocket.py) | API | Server → iOS push for note version updates | WS /ws/{session_id} | Latest note version | Memory (per connection) | Yes (JWT in connect param) | Built | Built | P1 | Done | M |  |  |  | B010 Notes | Stage 2 status push not yet on the wire — iOS polls. | Polling fallback already in place; WS extension can land post-pilot.
B015 | Note-gen providers (modules/providers/note_gen/) | Module | Pluggable note generation: OpenAI, Anthropic, Gemini behind a single base interface | openai.py, anthropic.py, gemini.py, base.py | — | — | n/a | Built | Built | P0 | Done | XL |  |  |  | B024 Provider registry | Gemini occasionally truncates structured JSON — prefer OpenAI/Anthropic for autonomous runs. | All routed through registry — no direct calls.
B016 | Vision providers (modules/providers/vision/) | Module | Vision providers for Stage 2 captioning | openai.py, anthropic.py, gemini.py, shared.py | — | — | n/a | Built | Built | P0 | Done | L |  |  |  | B024 Provider registry | — | —
B017 | Transcription providers (modules/providers/transcription/) | Module | Whisper + AssemblyAI providers behind shared interface | whisper.py, assemblyai.py | TranscriptSegment[] | — | n/a | Built | Built | P0 | Done | M |  |  |  | B024 Provider registry | — | —
B018 | Audit log service (modules/audit_log/) | Module | Append-only DynamoDB write of all session lifecycle, masking, export, purge, conflict events | write_event, query_events | Audit row (session, event_type, payload, ts) | DynamoDB | n/a | Built | Built | P0 | Done | M |  |  |  | M007 DynamoDB | — | No update/delete operations. Ever.
B019 | PHI audit service (modules/phi_audit/) | Module | Backend redaction proof + Comprehend Medical scan on transcripts | run_phi_audit | PHI hits | DynamoDB + S3 | n/a | Built | Built | P0 | Done | M |  |  |  | M012 Comprehend Medical | — | Logs to audit on every hit; never writes PHI to logs.
B020 | Cleanup service (modules/cleanup/) | Module | S3 TTL + Lambda-style cleanup for raw audio/frames; purge confirmation | schedule_purge, confirm_purge | Cleanup audit events | S3 + DynamoDB | n/a | Built | Built | P0 | Done | M |  |  |  | M006 S3, B018 audit-log | End-to-end purge lifecycle (P0-05) still partly client-driven; iOS already calls export-audit which transitions to EXPORTED. | Confirms raw data deletion every session.
B021 | Session state machine (modules/session/) | Module | 10-state machine + transition guards + consent hard-block | transition_session, InvalidTransitionError | SessionModel | PostgreSQL | n/a | Built | Built | P0 | Done | L |  |  |  | B018 audit-log | — | Hard-blocks record without consent_confirmed.
B022 | Note versioning service (modules/note_gen/) | Module | Immutable note versions per edit/resolve; approve marks vFinal | create_note_version, get_latest_note, approve_note, edit_note, resolve_conflict | NoteVersionModel, Note | PostgreSQL | n/a | Built (M-09 source anchoring + M-10 resolve_conflict) | Built | P0 | Done | L |  |  |  | B010 Notes API | — | —
B023 | Stage 2 job queue (modules/vision/jobs.py) | Module | Async Stage 2 lifecycle: pending → running → completed/failed with non-clobberable terminals (B-06) | create_job, mark_running/completed/failed, get_latest_job | Stage2JobModel | PostgreSQL | n/a | Built (B-06) | Built | P0 | Done | M |  |  |  | B011 Vision | Fire-and-forget task is dropped on process restart; no recovery sweep yet. | Recovery sweep is a post-pilot polish.
B024 | Provider registry (modules/config/provider_registry.py) | Module | Type-safe registry — never call AI providers directly | get_note_provider, get_vision_provider, get_transcription_provider | ProviderConfig | — | n/a | Built | Built | P0 | Done | M |  |  |  | M008 AppConfig | — | Drives < 30 s provider swap via AppConfig change.
B025 | Alembic migrations | Module | Production DB schema bootstrap + evolution (P0-04) | alembic init, versions/*.py for each model | All SQLA models | PostgreSQL | n/a | Not started — create_all only | Initial migration covering UserModel, SessionModel, TranscriptModel, NoteVersionModel, PilotMetricsModel, Stage2JobModel, CustomTemplateModel, PhysicianProfileModel. | P0 | Done | L |  |  |  | All B-* models | Blocks any prod-like deploy. | Use --autogenerate as starting point, then hand-tune for index/constraint ordering.
B026 | Persistent users + admin (P0-06) | Module | Replace _MOCK_USERS with SQL UserModel CRUD + Cognito sync | user CRUD, role change, deactivate | UserModel | PostgreSQL + Cognito | Yes | Mock in-memory store | Real persistence + audit on every role change. | P0 | Done | L |  |  |  | B001 Auth, B025 migrations | User edits must survive restart for compliance pre-pilot. | —
B027 | Persistent eval scoring (B-08) | Module | Persist eval review scores + frame/transcript/note linkage | create_eval_record, list_pending, save_score | EvalRecordModel (new) | PostgreSQL + S3 | Yes | In-memory stub | Persisted scoring + retention approval gate for eval team. | P1 | Done | M |  |  |  | B025 migrations | — | Eval Team + CTO access only.
B028 | End-to-end smoke test (P0-07) | Module | One-command verification of consent → record → Stage 1 → Stage 2 → review → approve → export → purge | scripts/e2e_smoke.py, pytest integration suite | — | — | n/a | Not started | Single docker-compose-driven test that exercises every audit-log event the pilot will produce. | P0 | Done | M |  |  |  | All backend modules | Needed for pilot acceptance. | Use existing seed_dev + LocalStack init script.
B029 | Patient + chart (B-01, deferred) | Module | Patient model + chart workspace relation | patient CRUD, chart link | PatientModel | PostgreSQL | Yes | Not started | Deferred post-pilot; web portal feature. | P3 | Not Started | L |  |  |  | B025 migrations | Confirm scoping with pilot — clinic-mode MVP doesn't need a patient model. | —
B030 | Schedule API (B-02, deferred) | Module | Appointment + visit-type model with session start link | appointment CRUD, start-session-from-appointment | AppointmentModel | PostgreSQL | Yes | Not started | Deferred post-pilot. | P3 | Not Started | L |  |  |  | B029 Patient | — | —
TOTAL (days)
REMAINING (days, excl. Done)
Note on C3: e.g. REST API, GraphQL, Worker, Scheduled job, gRPC, Auth service, Gateway
Note on M3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.

## Microservices & Integrations
Microservices, Wiring & Integrations
ID | Component / Integration Name | Kind | Purpose | From (consumer) | To (provider) | Protocol / Transport | External? (3rd party) | Auth / Secrets needed | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
M001 | OpenAI Whisper | AI provider | Audio → timestamped transcript | Backend (B007 Transcription) | OpenAI Whisper API + local whisper webservice fallback | HTTPS REST | Yes | API key (Secrets Manager) | Wired | Wired | P0 | Done | M |  |  |  | M013 Secrets Manager | Cost-control on long encounters — clip to MVP-relevant ranges. | Local docker whisper provides offline dev path.
M002 | AssemblyAI | AI provider | Fallback transcription provider with diarization | Backend (B007) | AssemblyAI | HTTPS REST | Yes | API key | Wired | Wired | P1 | Done | M |  |  |  | M013 Secrets Manager | — | Selected via AppConfig at runtime.
M003 | OpenAI GPT-4o | AI provider | Note generation (Stage 1 + Stage 2 merge) | Backend (B010 Notes) | OpenAI Chat Completions | HTTPS REST | Yes | API key | Wired | Wired | P0 | Done | M |  |  |  | B015 note-gen providers | Latency budget tied to 30 s Stage 1 SLA. | Currently the default per docker-compose.
M004 | Anthropic Claude Sonnet 4 | AI provider | Note generation alt + vision captioning | Backend (B010, B011) | Anthropic Messages | HTTPS REST | Yes | API key | Wired | Wired | P0 | Done | M |  |  |  | B015, B016 providers | — | Swap target via AppConfig — < 30 s.
M005 | Google Gemini 2.5 Flash | AI provider | Note generation alt + vision captioning | Backend (B010, B011) | Google Gemini API | HTTPS REST | Yes | API key | Wired | Wired | P1 | Done | M |  |  |  | B015, B016 providers | Truncates long structured JSON — avoid for autonomous runs. | Available for eval comparisons.
M006 | AWS S3 | AWS service | Raw audio + masked frames + screen frames + DOCX exports | Backend (B007/B008/B009/B012) | S3 (ca-central-1) | AWS SDK | No (AWS) | IAM via Cognito | Wired | Wired | P0 | Done | M |  |  |  | M010 KMS | — | TTL policies for raw audio (≤1 h) + frames (≤24 h after export).
M007 | AWS DynamoDB | AWS service | Append-only audit log | Backend (B018 audit-log) | DynamoDB | AWS SDK | No | IAM | Wired | Wired | P0 | Done | M |  |  |  | — | — | Enforces append-only at table policy.
M008 | AWS AppConfig | AWS service | Runtime provider + flag + threshold config (30 s polling) | Backend (B024 registry) | AppConfig | AWS SDK | No | IAM | Wired | Wired | P0 | Done | M |  |  |  | — | Schema validator must reject invalid keys pre-deploy. | Schema validation + audited deployment per Phase 8.
M009 | AWS Cognito | AWS service | JWT auth via JWKS | iOS + Backend (B001) | Cognito User Pool | OIDC JWT | No | Pool/client ID | Wired | Wired | P0 | Done | M |  |  |  | B026 user store | User-pool sync to UserModel pending P0-06. | —
M010 | AWS KMS | AWS service | Encryption keys for S3 + DynamoDB | Backend (all storage) | KMS | AWS SDK | No | IAM | Wired | Wired | P0 | Done | S |  |  |  | — | — | —
M011 | AWS Textract | AWS service | Server-side OCR for screen frames (fallback when on-device path returns low confidence) | Backend (B009 Screen) | Textract | AWS SDK (sync) | No | IAM | Wired | Wired | P0 | Done | M |  |  |  | — | Sync boto3 inside async def — wrap in asyncio.to_thread post-pilot. | On-device redaction happens first; Textract only sees redacted bytes.
M012 | AWS Comprehend Medical | AWS service | PHI entity scan over transcripts for the masking report | Backend (B019) | Comprehend Medical | AWS SDK | No | IAM | Wired | Wired | P0 | Done | M |  |  |  | — | — | —
M013 | AWS Secrets Manager | AWS service | Storage of OpenAI / Anthropic / Gemini / AssemblyAI keys | Backend (B015–B017) | Secrets Manager | AWS SDK | No | IAM | Wired | Wired | P0 | Done | S |  |  |  | — | — | API keys never called from iOS.
M014 | PostgreSQL | Data store | Sessions, transcripts, note versions, profiles, pilot metrics, Stage 2 jobs, eval (pending) | Backend | RDS PostgreSQL (prod) / postgres:15-alpine (dev) | asyncpg | No | DB password (Secrets Manager prod) | Wired | Wired | P0 | Done | M |  |  |  | B025 Alembic | Schema lives in models.py + create_all only; needs Alembic before prod. | —
M015 | Apple Vision framework | iOS framework | On-device face detection + blur, OCR-based screen redaction | iOS MaskingPipeline | Apple Vision | Native | No | — | Wired | Wired | P0 | Done | L |  |  |  | — | Fail-closed: a failed mask must never produce uploaded bytes (P0-01). | Backed by an extensive PHI regex bank + QA fixtures (M-04).
M016 | AVFoundation | iOS framework | Audio + video capture, PCM extraction, WAV build | iOS CaptureManager | AVFoundation | Native | No | Mic/Camera permissions | Wired | Wired | P0 | Done | L |  |  |  | — | Permission denial path tested on iPhone; QA on iPad still needed. | Mode-aware: skips video input when audioOnly.
M017 | ReplayKit | iOS framework | Screen recording for EMR/lab/imaging frames | iOS ScreenCaptureManager | ReplayKit | Native | No | Screen-recording user grant | Wired | Wired | P0 | Done | M |  |  |  | M015 Apple Vision | ReplayKit pause discards pre-pause frames — accepted for MVP. | Toggleable via feature_flags.screen_capture_enabled.
M018 | MediaPipe face detection (backup) | iOS framework | Secondary face detector for fallback / cross-check | iOS MaskingPipeline | MediaPipe | Native (CocoaPods / SPM) | Yes (Google) | — | Mostly wired | Confirm fallback path exercised in QA fixtures. | P2 | Not Started | S |  |  |  | M015 Apple Vision | Apple Vision is primary; MediaPipe only as cross-check. | —
M019 | Ray-Ban Meta SDK (M-03) | Wearable SDK | Glasses video/audio capture | iOS MetaWearablesSource | Meta SDK | BLE + native | Yes | Partner SDK + Meta access | Stubbed (notImplemented) | Deferred — pilot ships iPhone/iPad fallback. | P3 | Not Started | XL |  |  |  | M020 BLE pairing | Partner approval timeline unknown. | Stub throws CaptureSourceError.notImplemented.
M020 | BLE pairing (BLEPairingManager) | iOS framework | Bluetooth scan + pair flow for wearable / external audio | iOS WearableSetupView | CoreBluetooth | Native | No | Bluetooth permission | Wired (stubbed device list) | Wired | P2 | Done | M |  |  |  | M019 Meta SDK | — | —
M021 | WebSocket push (Backend ↔ iOS) | Real-time | Server pushes new note version to NoteReviewView mid-session | Backend (B014) | iOS WebSocketClient | WebSocket (RFC 6455) | No | JWT in connect param | Wired | Wired | P1 | Done | M |  |  |  | B010 Notes | Stage 2 status push not yet on the wire (iOS polls); add post-pilot. | —
M022 | iOS Keychain | iOS framework | Voice embedding + auth token storage | iOS KeychainHelper | Keychain | Native | No | — | Wired | Wired | P0 | Done | S |  |  |  | — | Voice embedding MUST never transmit — Keychain only. | —
M023 | iOS UserDefaults | iOS framework | Session persistence across crashes + consent metadata | iOS SessionPersistence | UserDefaults | Native | No | — | Wired (M-05 consent metadata persists too) | Wired | P1 | Done | S |  |  |  | — | — | Crash recovery validates server-side session state before re-adopting.
M024 | LocalStack | Dev infra | S3/DynamoDB/AppConfig/Cognito/KMS/Textract/Secrets Manager emulation for dev | Docker Compose | LocalStack | Docker network | No | Auth token | Wired (init script seeds S3 buckets + AppConfig) | Wired | P0 | Done | M |  |  |  | — | — | scripts/localstack-init/setup.sh seeds the env.
M025 | Terraform / HCL infra (Phase 8) | IaC | Provision ECS Fargate, RDS, DynamoDB, S3, KMS, Cognito, AppConfig, CloudWatch in ca-central-1 | Operator | AWS | Terraform CLI | No | AWS admin | Built (per memory) | Validate plan against pilot infra before cutover. | P0 | Done | L |  |  |  | M006–M013 AWS services | Per-env tfvars + remote state in S3+DynamoDB lock. | Re-confirmed in memory: IaC is Terraform, not CDK.
TOTAL (days)
REMAINING (days, excl. Done)
Note on C3: e.g. Microservice, Message Queue, Database, Cache, Object Storage, Auth Provider, Email/SMS, Payment Gateway, Analytics, Monitoring, CI/CD
Note on N3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.