## Instructions
MVP Solution Architecture & Effort Sizing — Instructions
| Purpose | This workbook captures the solution architecture for an MVP and produces an effort estimate based on a single developer's inventory. Fill the yellow cells. Green cells calculate automatically. The Effort Summary sheet rolls up totals.
| How to use | 1. Fill the Project Info sheet (project name, dates, demo target). 2. List every Screen on the Screens sheet — purpose, functionality, current vs target state. 3. List every Backend Service / API on the Backend Services sheet. 4. List every Microservice and Integration on the Microservices & Integrations sheet. 5. For each item, set Status and Complexity. Estimated Days auto-fills from Complexity. 6. Override the Estimated Days column manually whenever you have a better number. 7. Review the Effort Summary sheet — it aggregates the entire workbook.
Color legend
| Yellow | Input cell — fill this in.
| Green | Calculated — formula will fill it for you.
| Status values | Not Started • In Progress • Blocked • Done Use the dropdown in the Status column.
| Complexity scale | S = Small, ~1 dev-day (trivial change, simple CRUD endpoint, basic screen) M = Medium, ~3 dev-days (standard feature with some logic) L = Large, ~8 dev-days (multi-component feature, non-trivial integration) XL = X-Large, ~15 dev-days (new service, complex flow, heavy unknowns) These defaults are conservative for a single developer. Override the Estimated Days column whenever you have a better number from a spike or prior experience.
| Tip | If a row represents work that is already Done, set Status = Done. Done items are excluded from the 'Remaining' totals on the Effort Summary so you can see exactly how much is left to reach the demo.

## Project Info
Project Information
Project / MVP name
Developer (owner)
Today's date
Target demo date
Working days available
Demo audience / stakeholder
Primary business goal
In-scope for demo (one line)
Explicitly out-of-scope
Tech stack (frontend)
Tech stack (backend)
Hosting / infra
Known risks / unknowns
Current State → Target State (high-level narrative)
Current state
Target state for demo
Gap (what must be built)

## Effort Summary
Effort Summary — Rolled Up
Area | Items planned | Items done | Total effort (days) | Remaining (days) | % remaining | % remaining
| Screens | 0 | 0 | 0 | 0 | 0%
| Backend Services | 0 | 0 | 0 | 0 | 0%
| Microservices & Integrations | 0 | 0 | 0 | 0 | 0%
| GRAND TOTAL | 0 | 0 | 0 | 0 | 0%
Calendar conversion
| Buffer / contingency % | 20% | default 20% — edit to your taste
| Productive days / week | 4 | meetings/email eat the rest
| Remaining effort (days) | 0
| With buffer (days) | 0
| Calendar weeks needed | 0
Note: All numbers on this sheet are formulas pulling from the other tabs. Update the source sheets and these totals update automatically.

## Screens
Screens — UI Inventory
ID | Screen Name | User / Role | Purpose | Key Functionality (bullets) | Inputs / Data shown | Backend services it calls | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
S001 | [11 empty] | 0 |  | 0
S002 | [11 empty] | 0 |  | 0
S003 | [11 empty] | 0 |  | 0
S004 | [11 empty] | 0 |  | 0
S005 | [11 empty] | 0 |  | 0
S006 | [11 empty] | 0 |  | 0
S007 | [11 empty] | 0 |  | 0
S008 | [11 empty] | 0 |  | 0
S009 | [11 empty] | 0 |  | 0
S010 | [11 empty] | 0 |  | 0
S011 | [11 empty] | 0 |  | 0
S012 | [11 empty] | 0 |  | 0
S013 | [11 empty] | 0 |  | 0
S014 | [11 empty] | 0 |  | 0
S015 | [11 empty] | 0 |  | 0
S016 | [11 empty] | 0 |  | 0
S017 | [11 empty] | 0 |  | 0
S018 | [11 empty] | 0 |  | 0
S019 | [11 empty] | 0 |  | 0
S020 | [11 empty] | 0 |  | 0
S021 | [11 empty] | 0 |  | 0
S022 | [11 empty] | 0 |  | 0
S023 | [11 empty] | 0 |  | 0
S024 | [11 empty] | 0 |  | 0
S025 | [11 empty] | 0 |  | 0
[11 empty] | TOTAL (days) | 0 |  | 0
[11 empty] | REMAINING (days, excl. Done) |  |  | 0
Note on L3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.

## Backend Services
Backend Services & APIs
ID | Service / Module Name | Type | Purpose | Endpoints / Functions (list) | Data model / entities | Data store | Auth required? | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
B001 | [12 empty] | 0 |  | 0
B002 | [12 empty] | 0 |  | 0
B003 | [12 empty] | 0 |  | 0
B004 | [12 empty] | 0 |  | 0
B005 | [12 empty] | 0 |  | 0
B006 | [12 empty] | 0 |  | 0
B007 | [12 empty] | 0 |  | 0
B008 | [12 empty] | 0 |  | 0
B009 | [12 empty] | 0 |  | 0
B010 | [12 empty] | 0 |  | 0
B011 | [12 empty] | 0 |  | 0
B012 | [12 empty] | 0 |  | 0
B013 | [12 empty] | 0 |  | 0
B014 | [12 empty] | 0 |  | 0
B015 | [12 empty] | 0 |  | 0
B016 | [12 empty] | 0 |  | 0
B017 | [12 empty] | 0 |  | 0
B018 | [12 empty] | 0 |  | 0
B019 | [12 empty] | 0 |  | 0
B020 | [12 empty] | 0 |  | 0
B021 | [12 empty] | 0 |  | 0
B022 | [12 empty] | 0 |  | 0
B023 | [12 empty] | 0 |  | 0
B024 | [12 empty] | 0 |  | 0
B025 | [12 empty] | 0 |  | 0
B026 | [12 empty] | 0 |  | 0
B027 | [12 empty] | 0 |  | 0
B028 | [12 empty] | 0 |  | 0
B029 | [12 empty] | 0 |  | 0
B030 | [12 empty] | 0 |  | 0
[12 empty] | TOTAL (days) | 0 |  | 0
[12 empty] | REMAINING (days, excl. Done) |  |  | 0
Note on C3: e.g. REST API, GraphQL, Worker, Scheduled job, gRPC, Auth service, Gateway
Note on M3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.

## Microservices & Integrations
Microservices, Wiring & Integrations
ID | Component / Integration Name | Kind | Purpose | From (consumer) | To (provider) | Protocol / Transport | External? (3rd party) | Auth / Secrets needed | Current State | Target State for Demo | Priority | Status | Complexity | Estimated Days | Manual Override (Days) | Effective Days | Dependencies | Risks / Open Questions | Notes
M001 | [13 empty] | 0 |  | 0
M002 | [13 empty] | 0 |  | 0
M003 | [13 empty] | 0 |  | 0
M004 | [13 empty] | 0 |  | 0
M005 | [13 empty] | 0 |  | 0
M006 | [13 empty] | 0 |  | 0
M007 | [13 empty] | 0 |  | 0
M008 | [13 empty] | 0 |  | 0
M009 | [13 empty] | 0 |  | 0
M010 | [13 empty] | 0 |  | 0
M011 | [13 empty] | 0 |  | 0
M012 | [13 empty] | 0 |  | 0
M013 | [13 empty] | 0 |  | 0
M014 | [13 empty] | 0 |  | 0
M015 | [13 empty] | 0 |  | 0
M016 | [13 empty] | 0 |  | 0
M017 | [13 empty] | 0 |  | 0
M018 | [13 empty] | 0 |  | 0
M019 | [13 empty] | 0 |  | 0
M020 | [13 empty] | 0 |  | 0
M021 | [13 empty] | 0 |  | 0
M022 | [13 empty] | 0 |  | 0
M023 | [13 empty] | 0 |  | 0
M024 | [13 empty] | 0 |  | 0
M025 | [13 empty] | 0 |  | 0
[13 empty] | TOTAL (days) | 0 |  | 0
[13 empty] | REMAINING (days, excl. Done) |  |  | 0
Note on C3: e.g. Microservice, Message Queue, Database, Cache, Object Storage, Auth Provider, Email/SMS, Payment Gateway, Analytics, Monitoring, CI/CD
Note on N3: S=1d, M=3d, L=8d, XL=15d. Use override column if you need a different number.