## Overview
AURION — Effort Estimation v5 (Consolidated)
Mobile + Web Portal + Backend + Infra + Production Rollout. Reconciled 2026-05-22. Claude-Code-Days reflects the autonomous workflow pace (AURION-CODING-WORKFLOW.md), not human-dev pace.
LEGEND
🟢 Done | Shipped + verified. Commit SHA in Notes column.
🟡 Verify | Code shipped; needs end-to-end verification before claiming Done.
🟠 Not Started | MVP scope. 0% built.
🔴 Blocker | Hard prerequisite for the next phase. Resolve first.
🔵 In Progress | Partial — some sub-tasks shipped, others pending.
🟣 Future | Out-of-MVP. Estimated for visibility but not in pilot path.
ROLL-UP BY LANE
Lane | Items | Done | Verify | Not Started | Blocker | Future | Human-Days Remaining | Claude-Days Remaining
Mobile (iOS) | 37
Web Portal | 27
Backend Services | 44
Infrastructure / AWS | 24
Production Rollout | 5
External Blockers | 8
GRAND TOTAL
CRITICAL PATH TO PILOT
Backend physician workflow (WB20 → WB21 → WB22 → WB24, serial) | ~6 days
Web frontend physician workflow (W021 → W028 → W029, after backend ready) | ~8 days
Web admin polish + Amplify + Prod Phase 4-5 (parallel) | ~3 days
Tests + go-live gate | ~2 days
iOS polish + Config.swift dev/prod swap | ~1 day
CRITICAL PATH TOTAL (with lane parallelism) | ~13 working days
EXTERNAL BLOCKERS (calendar, NOT engineering)
Apple Dev activation | DONE 2026-05-22
Domain delegation (Cloudflare) + Phase 2 apply | ~1 day
Initial Phase 2 full apply + smoke test | ~1 day
Pilot physician onboarding + TestFlight invites | ~2-3 days
DPIA + consent forms + clinical safety committee sign-off | ~2-4 weeks
Pilot-ready calendar estimate | 5-7 weeks from 2026-05-22 → 2026-06-26 to 2026-07-10
Demo target | 2026-07-15 (~1 week buffer)
CLAUDE-CODE-PACE CONVERSION (observed in this build session)
S (1d human) → 0.1–0.25 Claude-d | Single-file edits, small refactors, config swaps.
M (3d human) → 0.5–0.75 Claude-d | Multi-file refactors, new endpoints, screen scaffolds.
L (8d human) → 1.0–2.0 Claude-d | Cross-cutting features, new modules, integration work.
XL (15-24d human) → 2.5–5.0 Claude-d | Net-new screens with state machine + tests (W028 Visit Workspace is the upper bound).
External blockers (Apple, DNS, IRB, insurance) | No compression. Wall-clock dominated.

## Mobile
MOBILE — iOS App
Lane: Mobile (iOS) · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
S001 | SplashView | 🟢 Done | S | 1 | 0.25 | Built. UI-P1 token refresh applied. | —
S002 | AuthView + LoginView + RegisterView | 🟢 Done | M | 3 | 0.5 | Built. UI-P6 toast → material. | B001 Auth
S003 | BiometricConsentView | 🟢 Done | S | 1 | 0.25 | biometric_consent_confirmed audit event wired. | —
S004 | VoiceExplanationView | 🟢 Done | S | 1 | 0.25 | Built. | —
S005 | VoiceRecordingView | 🟢 Done | L | 8 | 1.5 | Built (M-01 reconciled embedding dims). Raw audio purged immediately. | —
S006 | VoiceProcessingView | 🟢 Done | M | 3 | 0.5 | 128-dim MFCC → Keychain only. Embedding never transmitted. | S005
S007 | WearableSetupView | 🟢 Done | M | 3 | 0.5 | iPhone fallback path; Ray-Ban Meta deferred. | M019 Meta SDK (deferred)
S008 | OnboardingFlowView | 🟢 Done | M | 3 | 0.5 | Step orchestration + accessibility passes. | S003–S007
S009 | PhysicianProfileSetupView | 🟢 Done | M | 3 | 0.5 | iPad-adaptive (UI-P6). | B002 Profile
S010 | MainTabView | 🟢 Done | S | 1 | 0.25 | UI-P2 native TabView + iPad sidebarAdaptable. | S011, S013, S017
S011 | DashboardView | 🟢 Done | M | 3 | 0.5 | M-07 Stage 2 tile; readable-measure clamp (UI-P6). | B006, B010, M021
S012 | CaptureView | 🟢 Done | XL | 15 | 3 | M-02/M-05/M-06 done. Live Activity start/pause/resume wired (UI-P4b). | Apple Vision, AVFoundation, ReplayKit
S013 | DeviceHubView | 🟢 Done | M | 3 | 0.5 | UI-P6 iPad clamp + a11y labels. | M020 BLE
S014 | PostEncounterView | 🟢 Done | M | 3 | 0.5 | Built. | B010 Notes
S015 | ProcessingView (in ContentView) | 🟢 Done | L | 8 | 1.5 | Stage 1 SLA + retry surface. | B007, B010
S016 | NoteReviewView | 🟢 Done | XL | 15 | 3 | M-09 source anchoring, M-10 conflicts, conflicts banner pulse (UI-P5), Stage 2 gate fix. | B010, B011
S017 | ExportView | 🟢 Done | L | 8 | 1.5 | On-device DOCX + Plain Text. PDF deferred. | B012, M015
S018 | NoteReadyView | 🟢 Done | S | 1 | 0.25 | Built. | S014, S015
S019 | SessionsInboxView | 🟢 Done | M | 3 | 0.5 | Search + filter + iPad clamp + value-based deep-link push. | B006
S020 | SessionNoteView | 🟢 Done | M | 3 | 0.5 | Spotlight NSUserActivity donation (UI-P4a). | B010
S021 | ProfileView | 🟢 Done | M | 3 | 0.5 | Voice profile mgmt + iPad-adaptive. | B002
S022 | FrameGalleryView (debug) | 🟢 Done | S | 1 | 0.25 | Hidden in release per #if DEBUG. | —
S023 | ContentView (root shell) | 🟢 Done | M | 3 | 0.5 | Root routing + scene-phase purge hook + onContinueUserActivity / onOpenURL. | S001, S002, S008
UI-P1 | Color token sweep + semantic typography | 🟢 Done | M | 3 | 0.25 | Merged 2026-05-19 (commit 3a0152a). | —
UI-P2 | Native TabView + iPad sidebarAdaptable | 🟢 Done | M | 3 | 0.25 | Merged 2026-05-19 (commit 312d3fe). | —
UI-P3 | Inbox search + iPad clamp + amber conflicts banner | 🟢 Done | L | 8 | 0.5 | Merged 2026-05-19 (commit 40b3dcf). | S019, S016
UI-P4a | App Intents + Spotlight integration | 🟢 Done | M | 3 | 0.5 | StartSessionIntent + ShowPendingNotesIntent + AppNavigation bus (commit df32abb). | —
UI-P4b | Live Activity (Lock Screen + Dynamic Island) + Widget | 🟢 Done | L | 8 | 1 | AurionWidgets extension added via xcodeproj Ruby gem. StartSessionWidget + Live Activity widget (commit ba4900c + 9f3cca0). | Apple Dev Program (now active)
UI-P5 | Accessibility labels + symbol effects + motion polish | 🟢 Done | M | 3 | 0.25 | Capture controls, sort, toolbar, conflicts pulse (commit 4d00062). | —
UI-P6 | Materials (regularMaterial) + iPad readable-measure pass | 🟢 Done | S | 1 | 0.25 | Merged 2026-05-19 (commit 9cefee6). | —
AUR-DESIGN-NAVY | Collapse aurionNavyLegacy → aurionNavy | 🟢 Done | S | 0.5 | 0.25 | Brand navy (#0C1B37) is canonical (commit d6a88d3). | —
AUR-DESIGN-DARK | Full dark mode (muted slate palette) | 🟢 Done | XL | 15 | 1 | Adaptive tokens, 56 navy-text → adaptive swap, drop preferredColorScheme(.light) (commit 0cf99c8). | AUR-DESIGN-NAVY
Q-04 | SessionUIState shim cleanup | 🟢 Done | S | 1 | 0.25 | Drop Bool shims (commit 69b317e). | —
BUNDLE-ID | Rebrand bundle ID → com.aurionclinical.aurion | 🟢 Done | S | 0.5 | 0.1 | Pre-TestFlight (commit 39c9404). | —
FASTLANE | fastlane CLI bootstrap + TestFlight lanes | 🟢 Done | M | 3 | 0.25 | Appfile + Fastfile (commit e4a9d7b). User runs `fastlane bootstrap` once. | Apple Dev active
M018 | MediaPipe face detection (backup) | 🟣 Future | L | 5 | 0.5 | Pilot follow-up — revisit only if clinical safety committee asks. | M015 Apple Vision
M019 | Ray-Ban Meta SDK | 🟣 Future | XL | 15 | 5 | Deferred post-pilot — pilot ships iPhone/iPad fallback. | Partner SDK access
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)

## Web Portal
WEB PORTAL — Admin + Physician
Lane: Web (Next.js) · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
W001 | Login / Auth (admin portal) | 🟢 Done | S | 1 | 0.25 | Real JWT cookie + role redirect. | B001
W002 | Dashboard — Pilot Metrics Overview | 🟢 Done | M | 3 | 0.5 | Real API + aggregated metrics. | /admin/metrics, /admin/sessions
W003 | Audit Log Viewer | 🟢 Done | M | 3 | 0.5 | DynamoDB stream + CSV export. | Audit log populated
W004 | PHI Masking Report | 🟢 Done | M | 3 | 0.5 | Real API + per-session breakdown. | Comprehend Medical pipeline
W005 | Provider Config Viewer | 🟢 Done | S | 1 | 0.25 | Read-only AppConfig fetch. | AppConfig live
W006 | Session List / Completeness | 🟢 Done | M | 3 | 0.5 | 11-state badge map + specialty filter. | /admin/sessions
W007 | User Management UI | 🟡 Verify | L | 8 | 1 | UI is final. Verify Cognito wiring after P0-06 (commit e7a5a90). Smoke test create/deactivate. | WB14 Cognito AdminUser
W008 | Eval Session List + Score Entry | 🟡 Verify | L | 8 | 1 | UI final. Verify EvalRecordModel persistence after B-08 refactor. | WB13 EvalRecordModel
W009 | Session Detail page | 🟠 Not Started | M | 3 | 0.5 | lib/api.ts has the getter; backend endpoint exists; page itself not built. | WB12 (Done)
W010 | Amplify Deployment + CORS Fix | 🔴 Blocker | M | 5 | 1 | Portal runs localhost:3000 only. No aws_amplify_app in TF. CORS still localhost-only. | —
W011 | Role-Based Navigation (Physician vs Admin) | 🟠 Not Started | M | 4 | 0.5 | Sidebar.tsx hardcoded to admin routes. Two-role guard pattern. | Cognito role claim; W020 landing target
W012 | TypeScript types (Patient/Appt/Visit/Schedule) | 🟠 Not Started | S | 2 | 0.5 | types/index.ts has 18 admin interfaces, zero physician. | WB20–WB22 contracts frozen
W013 | lib/api.ts physician API client | 🟠 Not Started | S | 2 | 0.5 | 20 admin functions exist; zero physician. | WB20–WB25 endpoint contracts
W014 | WebSocket client (real-time Stage 1/2) | 🟠 Not Started | M | 5 | 1 | Backend /ws/{session_id} exists; no WS library in web package.json. | W013, W028
W020 | Schedule — Today's View (Day + Week) | 🟠 Not Started | L | 10 | 2 | Landing page for physicians. Appointment cards + status badges. | WB21 Schedule API; W011 routing
W021 | Patient Workspace shell + Overview tab | 🟠 Not Started | L | 9 | 2 | Demographics + latest visit + unresolved items. | WB20, WB23
W022 | Patient Workspace — Appointments tab | 🟠 Not Started | M | 3 | 0.5 | Reuses shell; read-only history. | W021, WB21
W023 | Patient Workspace — Visits tab | 🟠 Not Started | M | 4 | 0.75 | 7 visit states + active drafts + approval state. | W021, WB22
W024 | Patient Workspace — Notes tab | 🟠 Not Started | M | 4 | 0.75 | Approved + draft + exported notes. | W021, WB24, WB25
W025 | Patient Workspace — Timeline tab | 🟠 Not Started | M | 3 | 0.5 | Longitudinal activity feed. | W021, WB23
W026 | Patient Workspace — Attachments tab | 🟠 Not Started | S | 2 | 0.5 | Minimal upload/list. No preview pipeline in MVP. | W021, S3 upload endpoint
W027 | Patient Workspace — Exports tab | 🟠 Not Started | S | 2 | 0.5 | Export history list. | W021, WB25
W028 | Visit Workspace / AI Documentation Review (CORE) | 🟠 Not Started | XL | 24 | 5 | CORE physician workflow. Real-time Stage 1/2 over WS + inline editing + approval. Largest single item. | W014, WB22, WB24, WB25
W029 | Conflict Resolution UI | 🟠 Not Started | L | 11 | 2 | ENRICHES/REPEATS/CONFLICTS panel. | W028, WB24
W090 | French Localization | 🟣 Future | L | 8 | 3 | Deferred post-pilot. i18n scaffolding needed first. | MVP strings externalised
W091 | Patient-Facing Portal | 🟣 Future | XL | 15 | 6 | Out of MVP — new audience + auth surface. | Patient identity/auth model
W092 | Advanced Analytics Dashboard | 🟣 Future | L | 8 | 2 | Pilot dashboard adequate. | Chart library selected
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)

## Backend
BACKEND SERVICES
Lane: FastAPI · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
B001 | Auth (api/v1/auth.py) | 🟢 Done | M | 3 | 0.5 | Cognito JWKS + JWT + dev seed (now @dataclass per Q-06). | —
B002 | Profile (api/v1/profile.py) | 🟢 Done | S | 1 | 0.25 | Physician profile CRUD. | —
B003 | Config (api/v1/config.py) | 🟢 Done | S | 1 | 0.25 | Runtime AppConfig. | M008 AppConfig
B004 | Admin (api/v1/admin.py — package split) | 🟢 Done | L | 8 | 1.5 | CQR-4 split into users/sessions/eval/metrics. Cognito wiring now real. | B025 Alembic
B005 | Privacy (api/v1/privacy.py) | 🟢 Done | M | 3 | 0.5 | PHI masking report + DSAR purge. | B018
B006 | Sessions (api/v1/sessions.py) | 🟢 Done | L | 8 | 1.5 | 10-state lifecycle + paper-consent metadata. | B021
B007 | Transcription (api/v1/transcription.py) | 🟢 Done | XL | 15 | 2.5 | Whisper / AssemblyAI via registry + speaker tags + Stage 1 SLA. | B015, M001
B008 | Frames (api/v1/frames.py) | 🟢 Done | M | 3 | 0.5 | MaskingProof required on upload. | B018
B009 | Screen (api/v1/screen.py) | 🟢 Done | L | 8 | 1.5 | B-05 + M-08 vertical slice. | B010, B019, M011
B010 | Notes (api/v1/notes.py) | 🟢 Done | XL | 15 | 2.5 | Stage 1/2 + approve-stage1 async dispatch (M-09, M-10, B-06). | B011, B022, B023
B011 | Vision (api/v1/vision.py) | 🟢 Done | XL | 15 | 2.5 | Stage 2 captioning + conflict detection. | B016 vision providers
B012 | Export (api/v1/export.py) | 🟢 Done | M | 3 | 0.5 | On-device + audit endpoint (B-09). | B020 Cleanup
B013 | Health (api/v1/health.py) | 🟢 Done | S | 1 | 0.25 | Liveness for ECS/ALB. | —
B014 | WebSocket (api/v1/websocket.py) | 🟢 Done | M | 3 | 0.5 | Server-side delivered. | B010
B015 | Note-gen providers (modules/providers/note_gen/) | 🟢 Done | XL | 15 | 2.5 | OpenAI + Anthropic + Gemini. | B024 registry
B016 | Vision providers (modules/providers/vision/) | 🟢 Done | L | 8 | 1.5 | OpenAI + Anthropic + Gemini. | B024 registry
B017 | Transcription providers (modules/providers/transcription/) | 🟢 Done | M | 3 | 0.5 | Whisper + AssemblyAI. | B024 registry
B018 | Audit log service (modules/audit_log/) | 🟢 Done | M | 3 | 0.5 | DynamoDB append-only + AuditEventType StrEnum (Q-01) + kwarg whitelist (Q-03). | M007 DynamoDB
B019 | PHI audit service (modules/phi_audit/) | 🟢 Done | M | 3 | 0.5 | Comprehend Medical scan + audit-on-hit. | M012 Comprehend Medical
B020 | Cleanup service (modules/cleanup/) | 🟢 Done | M | 3 | 0.5 | Purge lifecycle + audited confirmation. | M006 S3, B018
B021 | Session state machine (modules/session/) | 🟢 Done | L | 8 | 1.5 | 10-state + consent hard-block. | B018
B022 | Note versioning service (modules/note_gen/) | 🟢 Done | L | 8 | 1.5 | Immutable versions + approve marker + M-09 source anchoring. | B010
B023 | Stage 2 job queue (modules/vision/jobs.py) | 🟢 Done | M | 3 | 0.5 | Async pending→running→completed/failed (B-06). | B011
B024 | Provider registry (modules/config/provider_registry.py) | 🟢 Done | M | 3 | 0.5 | Type-safe; drives <30s AppConfig swap. | M008
B025 | Alembic migrations (P0-04) | 🟢 Done | L | 8 | 1.5 | Prod schema bootstrap + evolution (commit e330675). | All models
B026 | Persistent users + admin (P0-06) | 🟢 Done | L | 8 | 1.5 | _MOCK_USERS → SQL + Cognito (commit e7a5a90). | B001, B025
B027 | Persistent eval scoring (B-08) | 🟢 Done | M | 3 | 0.5 | EvalRecordModel + retention. | B025
B028 | End-to-end smoke test (P0-07) | 🟢 Done | M | 3 | 0.5 | in-process FastAPI + ASGITransport + SAVEPOINT rollback (commit 3835704). | All modules
Q-01 | AuditEventType StrEnum | 🟢 Done | M | 2 | 0.25 | Typo-safe audit event types (commit 5c26052). | —
Q-02 | privacy.py _purge_session_prefix extraction | 🟢 Done | S | 1 | 0.25 | Flattened purge nesting + metric count bugfix (commit ec3a318). | —
Q-03 | write_audit kwarg whitelist + strict mode | 🟢 Done | S | 1 | 0.25 | Runtime kwarg validator (commit d539a57). | Q-01
Q-05 | _to_uuid → core/uuids.py | 🟢 Done | S | 0.5 | 0.1 | 4 duplicate copies → 1 helper (commit bdb22c3). | —
Q-06 | _DevUser → frozen @dataclass | 🟢 Done | S | 0.5 | 0.1 | Pydantic → frozen dataclass (commit 5c5f1e9). | —
WB12 | GET /admin/sessions/{id} — Session Detail | 🟢 Done | M | 3 | 0.5 | Already covered by existing session detail endpoints; W009 page still missing. | —
WB20 | PatientModel + Patient CRUD API | 🟠 Not Started | L | 10 | 1.5 | Foundation for all physician workflow. | B025 Alembic
WB21 | AppointmentModel + Schedule API (Day/Week) | 🟠 Not Started | L | 10 | 1.5 | Powers W020. | WB20
WB22 | VisitModel + Visit CRUD + 7-state machine | 🟠 Not Started | L | 11 | 2 | Server-enforced 'one active visit' concurrency. CORE backend. | WB20, WB21
WB23 | Multi-Provider Continuity API | 🟠 Not Started | M | 5 | 0.75 | Nurse/resident observations feed. | WB22
WB24 | Note Approval + Conflict Gating API | 🟠 Not Started | L | 10 | 1.5 | Gate approve on unresolved CONFLICTS. | WB22
WB25 | Web-triggered Export API (DOCX + Plain Text) | 🟠 Not Started | M | 5 | 0.75 | Web parity with iOS export. | WB22
B029 | Patient + chart (B-01, deferred to web) | 🟣 Future | L | 8 | 0 | Subsumed by WB20. | —
B030 | Schedule API (B-02, deferred to web) | 🟣 Future | L | 8 | 0 | Subsumed by WB21. | —
WB90 | EMR / FHIR Integration | 🟣 Future | XL | 15 | 6 | Post-pilot major workstream. | FHIR resource mapping
WB91 | Billing Workflow API | 🟣 Future | L | 8 | 3 | Post-pilot. | Billing rules + payer integration
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)

## Infrastructure
INFRASTRUCTURE & AWS
Lane: Terraform/AWS · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
M001 | OpenAI Whisper | 🟢 Done | M | 3 | 0 | API via Secrets Manager. | M013
M002 | AssemblyAI | 🟢 Done | M | 3 | 0 | Selected via AppConfig. | M013
M003 | OpenAI GPT-4o (note gen + Stage 2) | 🟢 Done | M | 3 | 0 | Default per docker-compose. | B015
M004 | Anthropic Claude Sonnet 4 | 🟢 Done | M | 3 | 0 | Note + vision. | B015, B016
M005 | Google Gemini 2.5 Flash | 🟢 Done | M | 3 | 0 | Eval comparisons; truncates long JSON. | B015, B016
M006 | AWS S3 (audio/frames/eval/export) | 🟢 Done | M | 3 | 0 | KMS-encrypted, public blocked, lifecycle. | M010 KMS
M007 | AWS DynamoDB (audit log) | 🟢 Done | M | 3 | 0 | Append-only + PITR + deletion protection. | —
M008 | AWS AppConfig | 🟢 Done | M | 3 | 0 | 30s polling + schema validation. | —
M009 | AWS Cognito | 🟢 Done | M | 3 | 0 | JWT via JWKS. | B026
M010 | AWS KMS | 🟢 Done | S | 1 | 0 | All-services encryption. | —
M011 | AWS Textract (screen OCR) | 🟢 Done | M | 3 | 0 | On-device redact runs first. | —
M012 | AWS Comprehend Medical (PHI scan) | 🟢 Done | M | 3 | 0 | Audit on every hit. | —
M013 | AWS Secrets Manager | 🟢 Done | S | 1 | 0 | All AI provider keys. | —
M014 | PostgreSQL (RDS / docker) | 🟢 Done | M | 3 | 0 | Encrypted, 30d backup prod, multi-AZ var. | B025 Alembic
M015 | Apple Vision framework (face + OCR) | 🟢 Done | L | 8 | 0 | On-device fail-closed masking. | —
M016 | AVFoundation (capture) | 🟢 Done | L | 8 | 0 | Mode-aware audio/video. | —
M017 | ReplayKit (screen) | 🟢 Done | M | 3 | 0 | Feature-flagged. | M015
M020 | BLE pairing (BLEPairingManager) | 🟢 Done | M | 3 | 0 | Stubbed device list works. | —
M021 | WebSocket push (Backend ↔ iOS) | 🟢 Done | M | 3 | 0 | JWT-authenticated channel. | B010
M022 | iOS Keychain (auth token + voice embedding) | 🟢 Done | S | 1 | 0 | Embedding never transmits. | —
M023 | iOS UserDefaults (crash recovery) | 🟢 Done | S | 1 | 0 | M-05 consent metadata persists. | —
M024 | LocalStack (dev infra) | 🟢 Done | M | 3 | 0 | S3/DDB/AppConfig/Cognito seed script. | —
M025 | Terraform/HCL (Phase 8) | 🟢 Done | L | 8 | 0 | 13 .tf files in ca-central-1; remote state + dev/prod tfvars. | M006–M013
WM10 | AWS Amplify — web portal hosting | 🔴 Blocker | M | 4 | 1 | No aws_amplify_app in TF. Bundled into Prod Phase 4 work. | W010
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)

## Production Rollout
PRODUCTION ROLLOUT (5 phases)
Lane: Terraform/CI · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
P1 | Phase 1 — State bootstrap (S3 + DDB + KMS) | 🟢 Done | S | 0.5 | 0.25 | bootstrap/ module applied to dev (commit cd40d3d). Account 366034225426. | —
P2 | Phase 2 — TLS + DNS + WAF + SHA-pin | 🔵 In Progress | M | 1.5 | 1 | Code shipped (commit 352cc56). Route53 zone created. BLOCKED on Cloudflare DNS choice (A/B/C). | P1
P3 | Phase 3 — GitHub Actions CI/CD with OIDC | 🟢 Done | M | 1 | 0.5 | Workflows + IAM OIDC trust shipped (commit 2a0fd11). Awaits secrets after P2 apply. | P1
P4 | Phase 4 — Cognito MFA + SNS + alarms + CloudTrail + Flow Logs + KMS rotation | 🟠 Not Started | M | 1.5 | 1 | Includes 5 missing operational alarms, SNS topic, GuardDuty enable. | P2
P5 | Phase 5 — Runbooks + IAM Identity Center + backup-restore drill | 🟠 Not Started | M | 1 | 1.5 | Mostly markdown + 1 IAM rework. Pre-pilot human-gated. | P4
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)

## External
EXTERNAL BLOCKERS (non-engineering)
Lane: External · status as-of 2026-05-22
ID | Name / Description | Status | S/M/L/XL | Human-Days (P50) | Claude-Code-Days | Notes / Commit | Pre-requisites
EXT-01 | Apple Developer Program activation | 🟢 Done | — | 0 | 0 | Active 2026-05-22. Unblocks TestFlight, App IDs, Live Activity push (if added). | —
EXT-02 | Cloudflare DNS delegation decision | 🔴 Blocker | — | 0 | 0 | Three paths on the table (manual records / subdomain delegation / Cloudflare TF provider). Recommend subdomain delegation. | —
EXT-03 | First Phase 2 full apply against dev | 🟠 Not Started | — | 0 | 0 | ~15-20 min compute + ~5 min cert validation post-DNS delegation. | EXT-02
EXT-04 | TestFlight initial build review | 🟠 Not Started | — | 0 | 0 | Apple reviews first build before internal testers can install. 24-48h. | fastlane bootstrap; first iOS push
EXT-05 | Cognito MFA enrollment by pilot physicians | 🟠 Not Started | — | 0 | 0 | ~5 min per physician via Cognito hosted UI. | P4 (MFA enable)
EXT-06 | DPIA + consent forms + clinical safety committee sign-off | 🔴 Blocker | — | 0 | 0 | NON-ENGINEERING. 2-4 weeks of calendar depending on pilot site's IRB/QI committee cadence. | —
EXT-07 | Cyber insurance + Business Associate Agreements (if applicable) | 🔴 Blocker | — | 0 | 0 | NON-ENGINEERING. Weeks. Required before live PHI. | —
EXT-08 | Pilot consent + recruitment of 3-5 physicians | 🟠 Not Started | — | 0 | 0 | Dr. Perry + Dr. Marie confirmed. Other 1-3 pending. | —
TOTALS
REMAINING (not 🟢 Done, excl. 🟣 Future)